Technical Design & Build Specification

AI-First Operations Platform — Textile Wholesale & Manufacturing, Surat

Engineering blueprint, technology stack, data model, and full cost model

Scale assumption: 15–20 cameras, 300–500 photo captures/day (medium)

Vision approach: Cloud multimodal LLM (Claude), architected hybrid-ready

CCTV: Edge vs Cloud cost comparison included

Status: Draft v1 for technical sign-off    Date: June 2026

All prices verified against current (June 2026) vendor rates. USD→INR at ₱83/$ for indicative local budgeting.

# 1. Scope & Engineering Assumptions

This document translates the approved high-level design into a buildable specification with costs. It assumes the three core capabilities: photo-based capture (stock + job-card folding), the AI brain (auto-reports + chat over firm history), and camera-based worker efficiency monitoring.

## 1.1 Locked assumptions (from client)

| Parameter | Assumed value (adjust if wrong) |
| --- | --- |
| Vision capture method | Cloud multimodal LLM (Claude Sonnet 4.6) per photo; code abstracted so a hybrid OCR-first path can be slotted in later without rework |
| Daily capture volume | 400 captures/day average (incoming + job cards + outgoing), ~12,000/month |
| Cameras | 18 cameras / workstations for monitoring |
| CCTV deployment | Costed both ways: on-site edge box vs cloud GPU (Section 8) |
| Users | 1 owner, 3–4 supervisors, 15–25 workers (capture only) |
| Languages on documents | Mixed printed + handwritten Gujarati/Hindi numerals (drives human-confirm rate) |
| Currency | Costs in USD with INR at ₱83/$ |

# 2. System Architecture

Three input channels feed one central backend and database. AI services are isolated as independent modules so each can scale, fail, or be swapped without touching the others.

## 2.1 Layered view

| Layer | Responsibility & components |
| --- | --- |
| Capture clients | Mobile/tablet PWA for workers (camera capture, one-tap confirm); web app for owner/supervisors (dashboards, chat, flags) |
| API / Backend | Node.js + TypeScript (NestJS) REST/WS API; auth, role enforcement, business rules, orchestration of AI services |
| AI services | (a) Vision Capture service → Claude API; (b) Brain/Agent service → text-to-SQL + retrieval over history; (c) CCTV Analytics service → YOLO-class detection + activity classification |
| Data layer | Supabase (Postgres) as source of truth; object storage for photos/clips; pgvector for history retrieval; Redis for queues/cache |
| Infra | Cloud app hosting; edge box OR cloud GPU for CCTV (Section 8); nightly batch job for daily report |

## 2.2 Why this shape

- Database is the single source of truth — the LLM never ‘remembers’ figures; it queries Postgres so every answer is auditable.

- AI services are stateless workers behind a queue — capture spikes (e.g. dispatch rush) are absorbed without dropping data.

- Vision is abstracted behind one interface — today it calls Claude; a hybrid OCR-first router can be inserted later purely as a config/strategy change.

# 3. Data Model (Core Tables)

Postgres schema. Every meter movement is a row, so stock, shortage, and efficiency are all derived from the same ledger and can never disagree.

| Table | Key fields | Purpose |
| --- | --- | --- |
| lots | lot_id, quality, design, grade, status | Master record per fabric lot |
| stock_movements | id, lot_id, direction(IN/OUT), meters, party, source_doc_id, ts | The ledger — every in/out meter event |
| job_cards | id, lot_id, process, worker_id, meters_in, meters_out, shortage, status | Production stage; shortage auto = in − out |
| workers | id, name, section, role | Staff master |
| allotments | id, worker_id, job_card_id, meters_allotted, shift, date | Work assigned (for efficiency) |
| capture_events | id, photo_url, type, ai_json, confidence, status, confirmed_by | Every photo + what AI read + confirm state |
| efficiency_daily | worker_id, date, allotted, done, efficiency_pct, flagged | Derived daily; powers flags & report |
| cctv_activity | worker_id, station, active_pct, idle_min, ts | Camera signal, joined to output |
| chat_audit | id, user_id, question, sql_run, answer, ts | Every brain Q&A logged for trust |

Design note: capture_events stores the raw AI output and a confidence score before it is committed to stock_movements / job_cards. Low-confidence rows wait for one-tap confirm — this is the ‘solid-proof’ gate.

# 4. Module A — Photo-Based Capture

## 4.1 Flow

- Worker photographs challan / lot tag / folded-meter display in the PWA.

- Image uploaded to object storage; a capture job is queued.

- Vision service sends image + structured prompt to Claude Sonnet 4.6, requesting strict JSON (lot, quality, meters, doc type).

- Service validates JSON, attaches a confidence score.

- High confidence → auto-commits to ledger / job card. Low confidence → flagged for one-tap supervisor confirm.

## 4.2 Why Sonnet 4.6

Strong document-vision and structured-output reliability at $3 / $15 per million tokens (input/output). Haiku 4.5 ($1/$5) is used as a cheap pre-classifier to reject blurry/irrelevant photos before they reach Sonnet, cutting cost. Architecture stays hybrid-ready: a self-hosted OCR model can later handle clean printed challans, reserving the LLM for hard/handwritten cases.

## 4.3 Per-photo cost basis

A photo ≈ 1,200–1,600 image tokens + ~400 prompt tokens input; ~150 output tokens. Budget ~2,000 input + 150 output tokens per capture. Worked cost is in Section 7.

# 5. Module B — The Brain (Reports + Chat)

## 5.1 Daily report (automated)

A nightly scheduled job aggregates the day’s ledger, shortages, stock balance, and efficiency, then asks the LLM to write a plain-language summary. Delivered to dashboard + optional WhatsApp/email. No human assembles it.

## 5.2 Chat assistant (text-to-SQL + retrieval)

- Owner asks a question in plain language (English/Hindi/Gujarati).

- Brain translates it to a safe, read-only SQL query against Postgres (SELECT-only role, no writes).

- Query runs; results returned to the LLM, which phrases the answer and shows the underlying numbers.

- Long-horizon ‘why/history’ questions also pull relevant past records via pgvector retrieval.

Trust controls: read-only DB role, query whitelisting/validation, row limits, and full chat_audit logging of every question, the SQL it ran, and the answer.

## 5.3 Cost basis

Chat: ~3,000 input (schema + question + rows) + ~400 output tokens per turn. Daily report: ~8,000 input + ~1,200 output once per day. Prompt caching on the fixed schema cuts repeated input ~90%.

# 6. Module C — Camera-Based Worker Monitoring

The hardest and most sensitive module. Technically a continuous video-analytics pipeline; the efficiency signal is only trusted when fused with real job-card output.

## 6.1 Pipeline

- Person detection & tracking — a YOLO-class model per camera stream identifies and tracks workers at each station.

- Activity / idle classification — lightweight classifier estimates active vs idle time per worker per station.

- Output fusion — camera activity is joined with meters completed (job cards). A worker is flagged only when low activity AND low output coincide — this avoids punishing fabric inspection or legitimate pauses.

- Aggregation — written to cctv_activity and rolled into efficiency_daily for the report and flags.

Policy gate (must be agreed): the flag is a coaching/planning signal, not an automatic pay action. Define what is flagged, to whom, and retention period before go-live — labour-law and morale exposure otherwise.

## 6.2 Hardware/compute is the real cost driver

18 continuous video streams need sustained GPU inference. This is fundamentally different from the bursty, per-photo LLM calls, and is why Section 8 compares edge vs cloud explicitly.

# 7. AI API Cost Model (Vision + Brain)

Based on current June 2026 Claude rates: Sonnet 4.6 $3/$15, Haiku 4.5 $1/$5 per million tokens (input/output).

## 7.1 Monthly token volumes (medium scale)

| Workload | Volume / mo | Input tok | Output tok |
| --- | --- | --- | --- |
| Photo capture (Sonnet) | 12,000 | 24.0M | 1.8M |
| Blur pre-filter (Haiku) | 12,000 | 9.6M | 0.24M |
| Chat queries (Sonnet) | ~1,500 | 4.5M | 0.6M |
| Daily reports (Sonnet) | 30 | 0.24M | 0.04M |

## 7.2 Monthly cost (before & after caching)

| Workload | List cost/mo | With caching* | Notes |
| --- | --- | --- | --- |
| Photo capture (Sonnet) | $99.0 | $72 | prompt cached |
| Blur pre-filter (Haiku) | $10.8 | $8 | — |
| Chat (Sonnet) | $22.5 | $10 | schema cached |
| Daily reports (Sonnet) | $1.3 | $1 | — |
| TOTAL AI API / month | ~$134 | ~$91 | ≈₲7,500 |

*Prompt caching reuses the fixed system prompt/schema at ~90% lower input cost. Batch API (50% off) can further cut the nightly report and any non-real-time reprocessing.

Headroom: at double the volume (~800 captures/day) AI API is still only ~$180–190/mo with caching. This cost scales gently and is not the budget risk — CCTV compute is.

# 8. CCTV Compute — Edge vs Cloud

18 continuous streams of person-detection + activity classification. Two ways to run it; this is the single biggest cost decision in the project.

## 8.1 Option A — On-site edge box (recommended)

One or two NVIDIA Jetson Orin-class devices on the factory LAN run YOLO + activity models locally via DeepStream (multi-stream on one device). Video never leaves the premises — better privacy, no bandwidth cost, resilient to internet outages.

| Item | Cost | Type |
| --- | --- | --- |
| Jetson Orin NX / AGX-class box × 2 (multi-stream) | $1,600–$2,400 | one-time |
| Cameras (if new) × 18 @ ~$45 | ~$810 | one-time |
| NVR / switch / cabling / install | $600–$1,000 | one-time |
| Power + maintenance | ~$15/mo | recurring |
| Edge subtotal | ~$3,000–$4,200 one-time | + ~$15/mo |

## 8.2 Option B — Cloud GPU

Streams pushed to a cloud GPU instance running the same models. No upfront hardware, but a sustained GPU plus continuous video upload bandwidth runs every month, indefinitely.

| Item | Cost | Type |
| --- | --- | --- |
| Cloud GPU (mid-tier, ~$0.5–$1.0/hr, near-24×7) | $360–$720/mo | recurring |
| Video egress / ingest bandwidth (18 streams) | $60–$150/mo | recurring |
| Cameras + local NVR/switch | ~$1,400 | one-time |
| Cloud subtotal | ~$1,400 one-time | + $420–$870/mo |

## 8.3 Verdict

Edge wins for this use case. Cloud’s recurring $420–$870/mo overtakes the edge hardware’s one-time cost within ~6–10 months, and keeps charging forever. Edge also keeps worker video on-premises (privacy + labour-relations) and survives internet outages — important on a factory floor. Recommend edge unless the client wants zero upfront capex.

# 9. Hosting & Other Running Costs

| Service | Cost/mo | Notes |
| --- | --- | --- |
| Supabase (Pro) | ~$25 | Postgres + auth + storage + pgvector |
| App hosting (API + web) | ~$20–$40 | container host / VPS |
| Object storage (photos/clips) | ~$10–$25 | grows over time; lifecycle-expire clips |
| Redis / queue | ~$10 | managed small tier |
| WhatsApp/email delivery | ~$5–$15 | report push (optional) |
| Infra subtotal | ~$70–$115 | ≈₲5,800–₲9,500/mo |

# 10. Build Cost (One-Time Engineering)

Estimated effort for a small team (you + 1 developer + designer), phased. Ranges reflect India-market blended rates; adjust to your actual team cost.

| Workstream | Weeks | Effort | Includes |
| --- | --- | --- | --- |
| DB + backend + auth/roles | 3–4 | M | Schema, API, role model |
| Vision capture module | 3–4 | M | Claude integration, confirm flow |
| PWA capture + dashboards | 4–5 | L | Worker + owner UI |
| Brain (text-to-SQL + report) | 3–4 | M | Chat, retrieval, audit, nightly job |
| CCTV analytics + fusion | 5–7 | L | Detection, activity, edge deploy |
| Testing, hardening, pilot | 3–4 | M | On-floor pilot + fixes |
| Total elapsed (phased, overlapping) | ~16–20 wks |  | Phases 1–2 usable by ~wk 10 |

# 11. Total Cost Summary

## 11.1 One-time (with edge CCTV)

| Item | USD | INR ≈ |
| --- | --- | --- |
| Edge CCTV hardware + cameras + install | $3,000–$4,200 | ₲2.5–3.5L |
| Engineering build (if outsourced; ₹0 if in-house) | varies | team cost |
| One-time total (hardware only) | $3,000–$4,200 | ₲2.5–3.5L |

## 11.2 Recurring monthly (steady state, edge)

| Item | USD/mo | INR ≈/mo |
| --- | --- | --- |
| AI API (vision + brain, cached) | ~$91 | ₲7,500 |
| Hosting + storage + queue | ~$70–$115 | ₲5,800–₲9,500 |
| Edge power/maintenance | ~$15 | ₲1,250 |
| Recurring total | ~$175–$220/mo | ≈₲14,500–₲18,000/mo |

Cloud-CCTV alternative: drop the one-time edge hardware, add ~$420–$870/mo, pushing recurring to ~$600–$1,090/mo (≈₲50,000–₲90,000/mo). This is why edge is recommended.

# 12. Recommended Delivery Phases

- Phase 1 (wk 1–10): DB + vision capture + dashboards + daily report. Delivers ‘no manual entry’ immediately. Recurring cost in this phase ~$110–150/mo, zero CCTV capex.

- Phase 2 (wk 8–12): Brain chat assistant over the now-accumulating history.

- Phase 3 (wk 12–20): CCTV monitoring + edge deploy + output fusion. Triggers the hardware capex — deferred until output data exists to validate flags.

# 13. Key Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| Handwritten/faded challans misread | Confidence gate + one-tap confirm; later hybrid OCR for clean docs |
| CCTV idle-detection unreliable alone | Fuse with job-card output; flag only when both agree |
| Worker pushback on monitoring | Agree policy upfront; coaching not punitive; on-prem video |
| AI cost creep at higher volume | Haiku pre-filter, prompt caching, batch; hybrid OCR path ready |
| LLM wrong/hallucinated answer | Read-only SQL, query validation, show source rows, full audit log |
| Internet outage halts floor | Edge CCTV runs offline; capture queues locally and syncs |

Next step: confirm edge vs cloud for CCTV and the daily volume, and we finalise the implementation plan and sprint breakdown.